Strategic Plan Implementation Action Plan

| STRATEGIC INITIATIVE: ESU personnel are essential and valuable assets of the University. Hence their knowledge and skills, creativity, and enthusiasm must be continuously supported and strategically developed to advance the University’s vision and mission. Goal: encourage, support and acknowledge faculty and staff. |  |  |  |  |
| --- | --- | --- | --- | --- |
| ACTIONS | WHO | WHEN | EXPECTED OUTCOME | NEW RESOURCE (If Applicable) |
| - Gap analysis of existing divisional strategic plans seeking input from units across campus to review their plans and report back on elements related to “PEOPLE”. - Provide support to divisions and departments in developing action items related to “PEOPLE” goals. - Conduct campus needs assessment to determine professional development and training opportunities most needed by university employees. - Develop additional ways and opportunities to recognize employee contributions to the university. - Utilize Employee Satisfaction Survey recommendations to address issues of concern to “People” on campus. | Divisional Directors and Academic Deans Implementation Team members Implementation Team Members and Institutional Effectiveness Implementation Team and Human Resources Management Implementation Team, Bonnie Green, campus constituent groups | January 17, 2011 February 1, 2011 March 2011 Spring 2011 Fall 2011 | Assess what units have determined to be important relative to “PEOPLE” at ESU. Determine gaps and who may need assistance from the implementation team to incorporate goals and actions related to “People” in their divisional plans. Units will incorporate action items into existing plans that address the strategic plan goals related to “PEOPLE” Enhance training and professional development opportunities for “People” on campus. Greater participation and desired outcomes will be realized. Improve employee satisfaction and campus climate. Improve campus climate | Complete Complete |